## Sheet1
Project Title: Milestone 6 Release #: 0.6 Sprint #: 6
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 | As a user, I'd like to view product detail in a focused, modal element | Create modal element which displays book data via jQuery scripting | David & Daniel | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0
| 2 | As a developer, I'd like to have up to date documentation of the project | Update Site Map | Daniel | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
|  |  | Update UML diagrams | Daniel | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  |  | Update project plan written document | Daniel | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
|  |  | Add update view handler and add /about page | Daniel | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 3 | As a developer, I'd like to have a list of test cases | Create auth and product test cases | Daniel | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 10.5 | 9 | 7.5 | 6 | 4.5 | 3 | 1.5 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 0