## Sheet1
Project Title: Milestone 7 Release #: 0.7 Sprint #: 7
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 | As a user, I'd like to view this site responsively on my phone/desktop/laptop/tablet | Update JSP pages to use proper Bootstrap classes | Daniel | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
| 3 | As a developer, I'd like to have complete documentation | Update project documentation and diagrams | Daniel | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 4 | 3.4286 | 2.8571 | 2.2857 | 1.7143 | 1.1429 | 0.57143 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0