## Sheet1
Project Title: Milestone 5 Release #: 0.5 Sprint #: 5 REST Services
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 | I'd like to have a way of deleting my articles | Add option to delete owned articles in product display page or profile page | tim | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
|  | As a User I'd like to view posts | Add a viewPosts page that displays a post | tim |  |  |  | 1
|  |  | Connect delete button/feature to DAO service | tim | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | -1
| 2 | As a 3rd party dev, I'd like to consume data from this app via an API | Build 1st REST Service route | Marc | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
|  |  | Build 2nd REST Service Route | Daniel | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
| 3 | As a dev, I'd like to have designs for all pages and features | Update and submit wireframes for all pages |  | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
| 4 | As a dev, I'd like to have an updated project plan | Update Project plan and any UML/ER designs to match specifications |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 5 | As a dev, I'd like to have a system for collaboration and project tracking | Update all lists, kanban boards, or shared resources for team | Daniel | 1 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0.5
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 9.5 | 8.1429 | 6.7857 | 5.4286 | 4.0714 | 2.7143 | 1.3571 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 9.5 | 9.5 | 9.5 | 5 | 3 | 3 | 1 | 1