## Sheet1
Project Title: Milestone 3 Release #: 0.3 Sprint #: 3
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 | I'd like to have coherently styled web pages and central navigation | Update CSS stylesheets and create Navigation bar/component for layout | Marc | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
| 2 | I'd like to have a portal for creating blog articles | Create Product Creation XHTML layout and styling | Tim | 5 | 0 | 0 | 0 | 1 | 3 | 1 | 0 | 0
|  |  | Create product creation page controller and JSF data validation logic | Tim | 1 | 0 | 0 | 0 |  | 0 | 1 | 0 | 0
|  |  | Create product creation-related EJB beans | Daniel/Chance | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
|  |  | Create product storage (data access) EJB beans | Daniel/Chance | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| 3 | As a user, I'd like to have clean navigation around the app from any page | Implement navigation menu/bar for consistent layout | Marc | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
| 4 | As a dev, I'd like to use industry-standard tools for this app | Update Old Controllers to use EJB-style bean injections | Daniel/Chance | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| 5 | As a dev, I'd like to have designs for all pages and features | Update and submit wireframes for all pages |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | As a dev, I'd like to have an updated project plan | Update Project plan and any UML/ER designs to match specifications | Daniel | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 7 | As a dev, I'd like to have a system for collaboration and project tracking | Update all lists, kanban boards, or shared resources for team | Daniel | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 19 | 16.2857 | 13.5714 | 10.8571 | 8.1429 | 5.4286 | 2.7143 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 19 | 19 | 19 | 14 | 13 | 10 | 5 | 0