## Sheet1
Project Title: Milestone 4 Release #: 0.4 Sprint #: 4 Database Access
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 | I'd like to have a place to view all products/articles | Add browse.xhtml page where a dataTable or list of articles is accessible | Tim | 5 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 0
| 2 | I'd like to have a way to update my articles | Allow editing of articles on write.xhtml/edit.xhtml or applicable page | Tim | 3 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0
|  |  | Connect editing-enabled page to DAO service | Daniel | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
|  |  | Create product creation-related EJB beans | Daniel | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
|  |  | Create product storage (data access) EJB beans | Daniel/Marc | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| 3 | I'd like to have a way of deleting my articles | Add option to delete owned articles in product display page or profile page | (unimplemented) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Connect delete button/feature to DAO service | (unimplemented) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | As a dev, I'd like to have an abstracted service for manipulating a data store | Write Java JDBC-connected PostgreSQL DAO service | Marc | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
| 5 | As a dev, I'd like to have designs for all pages and features | Update and submit wireframes for all pages |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | As a dev, I'd like to have an updated project plan | Update Project plan and any UML/ER designs to match specifications | Daniel | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 7 | As a dev, I'd like to have a system for collaboration and project tracking | Update all lists, kanban boards, or shared resources for team | Daniel | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 20 | 17.1429 | 14.2857 | 11.4286 | 8.5714 | 5.7143 | 2.8571 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 20 | 20 | 20 | 20 | 17 | 15 | 7 | 0