## Sheet1
Project Title: Milestone 6 Release #: 0.6 Sprint #: Security Services
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 | A home page | Spruce up home page for a landing place for users after login | Tim | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
|  | Secure login | Update XML file for security configuration. | Tim | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
|  | login form | Create securityLogin.xhtml form using j_security | Tim | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
|  | login error page | Build a login error page | Tim | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| 2 | As a dev, I'd like to be able to view a JavaDoc generated from the current project. | Add missing JavaDoc tags to existing files. Generate new JavaDoc files. | Marc | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
| 3 | As a dev, I'd like to have designs for all pages and features | Update and submit wireframes for all pages |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | As a dev, I'd like to have an updated project plan | Update Project plan and any UML/ER designs to match specifications | Daniel | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
| 5 | As a dev, I'd like to have a system for collaboration and project tracking | Update all lists, kanban boards, or shared resources for team | Daniel | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
| 6 | As a dev, I'd like a Postman collection with tests for the 3rd-party app API routes | Create Postman collection and add test(s) for each of the 4 API routes | Daniel | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
| 7 | As a dev/stakeholder, I'd like a presentation of the app's design/features/dependencies | Milestone explanation | Tim | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
|  |  | App Feature Walkthrough | Tim & Marc | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
|  |  | Code Structure Walkthrough | Tim & Daniel | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
|  |  | Rest Services Walkthrough | Daniel | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  |  | Compile Walkthroughs and Edit Video | Daniel | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 9.5 | 8.1429 | 6.7857 | 5.4286 | 4.0714 | 2.7143 | 1.3571 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 8 | 8 | 8 | 8 | 8 | 7 | 1 | 0